CCASA ED Transition Timeline

| Event | Responsible Party | Date |
| --- | --- | --- |
| Resignation notice | Erin | Aug 14 |
| Board Chair/ED discuss departure | Lisa and Erin | Aug 18 |
| Board Chair appoints Transition Committee | Lisa | Aug 18 |
| Board Chair meets with Staff | Lisa and Erin | Aug 20 |
| ED announces departure publicly | Erin (review Lisa) | Aug 25 |
| Transition Committee holds organizing meeting – process, who does what, when, go over needs assessment, identify Key Stakeholders to receive assessment | Transition Committee | Aug 26 |
| Update Needs Assessment with Transition Committee feedback (put in Survey Monkey) | Erin | Aug 26 |
| Send Needs Assessment to Board, Staff, & Key Stakeholders for completion | Lisa (Erin will send emails) | Aug 27-28 |
| Needs Assessment deadline, Board Chair follows up to ensure completed | Lisa/Board, Staff, Key Stakeholders | COB Sept 2 |
| Board Chair and ED compile results of Needs Assessment and develop amended job description and job posting based on feedback on agency needs | Lisa and Erin | Sept 2-5 |
| Compile Needs Assessment themes, draft grading criteria and draft job posting to TC and IT for review. | Lisa and Erin | Prior to Sept 8 |
| Transition Committee holds planning session with Staff and Board, Board approves job posting, job description, posted salary range. Approve rating criteria for resume review. | Lisa/Transition Committee | Sept 8 (email approval by 9/10 if major edits) |
| Transition committee launches search – post position on Non Profit Job Board etc., email out, post in other locations. Open Until Filled. Applications will be given priority consideration if received by Sept 26 | Transition Committee | Sept 10/11 |
| Transition committee holds check-in meeting(s) to discuss how search is progressing, creates criteria for phone screening. | Transition Committee | Sept 12-26 |
| Board Chair and ED begin review of resumes as they come in – use approved criteria to review resumes | Erin and Lisa | Sept 12-26 |
| Board Chair and ED provide TC with first cut resumes as they come in. TC review within 2 days of receiving the resume. | Transition Committee | Sept 12-30 |
| Transition Committee reviews resumes and provides BC and ED with rank order/recommendations for phone screen | Transition Committee | Sept 12-Oct 1 (rolling) |
| Phone screen of top 10-15 candidates utilizing a pre-determined criteria (Erin will set up as they are determined) | Erin and a TC member | Sept 12-Oct 1 (rolling) |
| Narrow candidates to approx. 7 for one hour in person interviews | TC and ED | No later than Oct 1 |
| ED and CCASA staff set up one-hour interviews with 7 or so candidates (at least one TC member to be involved, conference call in if necessary). | Erin and CCASA Staff | W/O Oct 6 or before (rolling) |
| Transition committee holds second planning session with staff to go over results of one-hour interviews and determine top 2-3 candidates for in-person day long interviews | Erin and TC | W/O Oct 13 |
| Transition Committee invites candidates to office, plans interview days, contacts stakeholders, books rooms | Erin and TC (Lisa calls finalists to suggest dates) | End of W/O Oct 13 |
| Finalists visit office for one-day interview (staff meeting, Board meeting, stakeholder meeting and presentation, meeting with ED and BC?) Note: Karen out of office Oct 21-24 | Finalists/TC | W/O Oct 20 & Oct 27 |
| Transition Committee reviews feedback sheets from all who attended interviews | TC | Oct 30-31 |
| Transition Committee meets with staff to check in Note: All staff unavailable Nov. 3-7 b/c RTAP training | Transition Committee | Nov 1-3 |
| November Board meeting – discussion of ED search outcome | Lisa and TC | Nov 3rd |
| Offer is made to successful candidate | Lisa | Nov 4-5 |
| Transition committee plans on-boarding process (input from staff) | Transition Committee | 2nd week Nov |
| Announce new ED | Transition Committee | 2nd week Nov |
| Month of Nov – all hands on deck to cover | TC and staff |  |
| New ED starts work | – | Dec 1 |
| New ED and Board embark on orientation/post-hire process | Various Members of the Executive Committee and Staff | Dec |
| Board Retreat | Board/new ED/Lisa | Later Dec/Jan or Feb |
| Executive Director completes 90-day plan | Executive Director | Early to Mid-Feb |
| Board chair engages with ED in 90-day check-in review | Lisa and Executive Director | Mid- to late Feb |
| Executive committee conducts six-month evaluation of ED | Executive Committee | Mid- to late May |
| Executive committee conducts annual performance evaluation of ED | Executive Committee | Mid- to late Dec |